Strategic Planning process and timeline 2020-2023

Why a strategic plan is important for CCSL, what can happen if we don’t have a strategy?

- The organisation will become funder-led

- The organisation turns into a collection of projects

- You lose vision and end up focused only on survival

- You feel unable to say ‘no’ to ideas, opportunities and demands

- You want to be all things to all people

- Your organisation’s activities are only undertaken because you have always done them

- Your organisational culture becomes resistant to change

The strategic plan needs to be accompanied by an annual business plan.  This is because:

- Funders require it

- To understand the idea behind the organisation or the bid

- To see that the plan has been fully worked out

- To check that the organisation is being realistic

- To ensure the organisation has thought about the possible risk

- To check that the organisation has the capcity to deliver the plan

- To understand the longer-term picture

- To create confidence in the organisation

It sets out the track record of the organisation, and demonstrates that we have effective systems, people and processes in place to ensure we can deliver results.

- To help trustees keep a grip on reality

A proper plan helps us to ensure that the realities of the organisation in its present situation are taken into account and sets out clear steps for its implementation.

Strategic Planning Process

Page | 1

Recommended timeline for 2020 – 2023 Strategy, business and budget creation and approval

| Date | Activity |
| --- | --- |
| 9th October 2019 | Trustee & Management team Away Day to: - Review performance of 2017-2020 strategic plan; - Identify potential strategic pillars for 2020 – 2023 E.g. - Build Capacity - Grow income - Find a home - Recognise, celebrate and communicate |
| December 2019 | Test key strategic choices through: - Piloting pop up shop; - Consultation/ engagement with Carers; - Consultation/ engagement with potential partners – funders/ business |
| January 2020 W/c 13th | Organisation away day Agree strategic direction – finalise strategic pillars and goals Match against CSSL Theory of Change |
| February 2020 | Draft strategic plan, business plan and budget prepared |
| March 4th 2020 | Papers circulated to Board |
| March 11th 2020 | Trustee Board provides feedback on budget and business plan with amends/ sign off |
| March 17th 2020 | Amends completed and staff team informed, through team meeting |
| March 31st 2020 | Staff appraisals completed and targets set |
| April 2020 | Beginging of new strategic period and business plan |

Page | 2